Sprint Plan

JobAutoApply — 5-Day CLI Build

TOP G LABS LTD

JobAutoApply  |  Version 3.0 (CLI)  |  April 2026

# 1. Philosophy

Build the smallest end-to-end slice possible. Get something usable by Day 3 (Reed + Claude + ATS renderer = real CVs in hand). Add Indeed and LinkedIn on Day 4. Polish the review loop on Day 5. No scope creep.

# 2. Critical Path Reminder

Highest priority: The ATS-compliant DOCX renderer. Build it on Day 2 and validate against Jobscan before anything else. A non-compliant CV is worse than no CV.

# 3. Day 1: Foundations

Goal: Project setup, data models, SQLite, Master CV loading.

- Initialise Python package with pyproject.toml (use uv or Poetry).

- Add dependencies: typer, rich, httpx, playwright, python-docx, anthropic, pydantic, python-dotenv, tenacity.

- Create folder structure per build-order doc.

- Implement jobtool/models.py with full Pydantic models for MasterCV, Job, Application.

- Implement jobtool/db.py with SQLite schema creation and basic CRUD.

- Implement jobtool/config.py to load .env and define data paths.

- Implement `jobtool init` command — creates ~/.jobtool/ and runs schema.

- Implement `jobtool master-cv validate` command.

Day 1 Deliverable: Tool installs, `jobtool init` works, Master CV loads and validates.

# 4. Day 2: ATS-Compliant DOCX Renderer (CRITICAL)

Goal: Build the renderer and validate it against Jobscan before doing anything else.

- Implement jobtool/renderer/docx_renderer.py with render_cv() function.

- Write a fixture Master CV in tests/fixtures/sample-master-cv.json for testing.

- Generate a sample DOCX from the fixture.

- Open the sample in Microsoft Word and visually verify: single column, Arial 11/14/18, standard headings, no tables, no headers/footers, solid round bullets.

- Upload the sample to Jobscan and verify parse success with zero critical errors.

- Iterate on the renderer until parsing is clean.

- Implement jobtool/renderer/pdf.py using soffice subprocess.

- Add a regression test that renders the fixture and asserts no Table elements, no headers, no footers in the output.

Day 2 Deliverable: Renderer produces ATS-compliant DOCX + PDF. Jobscan parses it cleanly.

# 5. Day 3: Reed API + Claude Generation

Goal: End-to-end flow from search to generated CV for Reed jobs.

- Implement jobtool/scrapers/base.py — Scraper protocol.

- Implement jobtool/scrapers/reed.py using httpx.

- Implement `jobtool scrape` command — wires scrapers to DB.

- Implement jobtool/ai/prompts.py — CV and cover letter prompt templates from Master CV System doc.

- Implement jobtool/ai/tailor.py — generate_tailored_cv() and generate_cover_letter().

- Implement `jobtool generate <job_id>` command — loads job, calls tailor, renders DOCX+PDF, saves to DB.

- Test end-to-end with 5 real Reed jobs.

- Manually verify each generated CV passes Jobscan.

Day 3 Deliverable: Working end-to-end flow. User can scrape Reed, generate tailored CVs, and have them saved to disk.

# 6. Day 4: Indeed + LinkedIn Scrapers

Goal: Add browser-based scrapers with anti-detection.

- Implement `jobtool login <source>` command — opens Playwright in headed mode for manual login.

- Implement jobtool/scrapers/indeed.py using Playwright with persistent context.

- Test Indeed with 20+ real searches.

- Implement jobtool/scrapers/linkedin.py with stricter anti-detection (mouse jitter, longer delays).

- Test LinkedIn with 10+ real searches.

- Add de-duplication across sources in the scrape command.

Day 4 Deliverable: All 3 scrapers work reliably. Scrape produces de-duplicated job list across sources.

# 7. Day 5: Review Loop + Polish

Goal: Make the tool pleasant to use for daily application sprints.

- Implement jobtool/review.py — the interactive review loop.

- Use Rich panels for displaying jobs.

- Capture single keypresses with readchar or sys.stdin.

- Implement keyboard shortcuts: o, s, x, n, p, e, q.

- Auto-advance after s/x.

- Implement `jobtool list` and `jobtool history` commands.

- Implement `jobtool apply <url>` command for quick single-job applications.

- Final polish: error messages, progress bars, startup banner.

- Run a real application sprint: scrape, generate, review 30+ jobs.

Day 5 Deliverable: Tool is stable, pleasant to use, and ready for daily use.

# 8. Post-V1 Backlog

- V1.1: Cache generations to avoid re-running Claude for the same job.

- V1.2: Stats command (applied this week, response rate).

- V1.3: Export history to CSV.

- V1.4: Add more job boards (Totaljobs, CV-Library).

- V1.5: Simple TUI wrapper using Textual (optional, only if CLI feels too basic).

# 9. Risk Buffer

If any day overruns, cut LinkedIn from V1 and ship with Reed + Indeed only. LinkedIn is the highest-risk source and can be added in V1.1.